## Sheet1
Task | Email By | Email Date | Completion Date | Comment | Time Taken | Legends | Meaning
2021-11-01 | [6 empty] | Deployment on production
CBT - Technical & Functional | prashantk@chetu.com | Mon 11/1/2021 5:11 PM | Mon 11/1/2021 7:02 PM |  |  |  | Mail not includes Uddeshyas@chetu.com
Add S. No. | parulk@chetu.com | Tue 11/2/2021 8:08 PM | Tue 11/2/2021 8:20 PM |  |  |  | Deployment on QA/Staging
Issue in ATS | junaidh@chetu.com | Wed 11/3/2021 7:43 PM | Wed 11/3/2021 8:07 PM |  |  | Opening module>>Search Candidate>>Move to Offer issue | uddeshyas@chetu.com | Discussed in morning call on Wed 2/23/2022 6:30 PM
Deployed new release of ATS(production) |  |  | Fri 11/5/2021 6:57 PM
Addition of Trainee in New Resource Request | junaidh@chetu.com | Fri 11/5/2021 6:44 PM | Fri 11/5/2021 7:04 PM
Member not showing on ATS | sumits@chetu.com | Thu 11/11/2021 7:27 PM | Thu 11/11/2021 8:20 PM
Name not visible in Opening Management due to less width | vishalg@chetu.com | Mon 11/15/2021 9:34 PM | Mon 11/15/2021 10:01 PM
Update Job Description on ATS portal | ramakants@chetu.com | Fri 11/19/2021 8:55 AM | Fri 11/19/2021 10:09 PM
2021-12-01
rp407650@gmail.com to be shown on onboarding and Offer | sumits@chetu.com | Fri 12/3/2021 6:36 PM | Fri 12/3/2021 7:37 PM
Onboarding not showing - Rahul kumar 19 | deepikab2@chetu.com | Mon 12/6/2021 6:12 PM | Mon 12/6/2021 9:57 PM
Candidate name Change - Rima Srivastava | deepikab2@chetu.com | Thu 12/9/2021 7:02 PM | Thu 12/9/2021 10:02 PM
ATS Issue - (Priyanka and Manisha) | jyotid@chetu.com | Sat 12/11/2021 1:50:00 PM | Mon 12/13/2021 4:34 PM
Members not showing on OnBoarding | deepikab2@chetu.com | Tue 12/14/2021 4:09 PM | Tue 12/14/2021 5:34 PM
Deployed new release of ATS(production) |  |  | Mon 12/20/2021 10:46 PM
Status change for request id 64218 | uddeshyas@chetu.com | on call | Tue 12/21/2021 8:05 PM
ATS Status ISSUE | uddeshyas@chetu.com | Wed 12/15/2021 10:01 PM | Tue 12/21/2021 8:44 PM
Candidate is not showing offer management | deepikab2@chetu.com | Tue 12/21/2021 6:56 PM | Tue 12/21/2021 8:13 PM
Link livelavkushjaiswal@gmail.com to Opening Id 69343 | parulk@chetu.com | Tue 12/21/2021 9:07 PM | Tue 12/21/2021 10:08 PM
ATS Issue | jyotid@chetu.com | Fri 12/24/2021 5:57 PM | Fri 12/24/2021 6:19 PM
Resolved filter issue in Interviewer module,added number field |  |  | Fri 12/24/2021 7:40 PM
Modified Offer letter format | uddeshyas@chetu.com | Wed 12/8/2021 7:35 PM | Mon 12/27/2021 11:19 PM
2022-01-01
Deployed new release of ATS(production) | uddeshyas@chetu.com | Tuesday, January 4, 2022 3:54 PM | Thu 1/6/2022 7:24 PM | Deployed Location Zone & modified Excel sheet columns | 3 days
Offer Letter Email access | uddeshyas@chetu.com | Mon 1/10/2022 4:19 PM | Mon 1/10/2022 7:04 PM | Added two new emails in jobs team | 3 hours
Opening #68739 issue resolved | uddeshyas@chetu.com | Friday, January 14, 2022 5:20 PM | Fri 1/14/2022 5:39 PM |  | 20 min
ATS Registration | mayankr@chetu.com | Thursday, January 20, 2022 6:55 PM | Thu 1/20/2022 7:12 PM |  | 2 hours
ATS issue | sonalim2@chetu.com | Tuesday, January 25, 2022 8:16 PM | Thu 1/27/2022 4:50 PM |  | 2 hours
name spelling correction | ashudeepy@chetu.com | Friday, January 28, 2022 8:26 PM | Fri 1/28/2022 8:33 PM |  | 20 min
Deployed new release of ATS(QA/Staging) | uddeshyas@chetu.com |  | Fri 1/28/2022 8:17 PM | (AutoFollowUp First Phase)
2022-02-01
added new option in drop down of Location Zone in Offer Module | uddeshyas@chetu.com | Physical Meeting(same day-5:00 PM) | Fri 02/04/2022 7:20 PM
Jobs - Marketing Task - Part 2 | uddeshyas@chetu.com | Tue, February 1, 2022 1:50 PM | Tue 2/8/2022 7:27 PM | 3 days delay in Approving format | 5 days
Already Showing Tech Selected ! | deepikab2@chetu.com | Fri 2/11/2022 7:02 PM | Mon 2/14/2022 7:20 PM | Sat Off & Sunday | 2 hours
Joining Data not Showing on Report ! | anupc@chetu.com | Tue 2/15/2022 12:13 AM | Wed 2/16/2022 6:08 PM |  | 2 days
Employee reference | uddeshyas@chetu.com | Fri 2/18/2022 7:49 PM | Fri 04-03-2022 16:19 | Deployed Employ reference page on backbone | 4 days
#67516 #67868 | uddeshyas@chetu.com | Tuesday, February 22, 2022 7:24 PM | Tue 2/22/2022 8:34 PM |  | 2 hour
Track Candidate(module)>>Add Candidate >>State and city dropdown issue | uddeshyas@chetu.com | Tue 2/22/2022 11:44 PM | Wed 2/23/2022 8:09 PM | Ticket Name-ATS issue | 1 hour
Resourcing (module)>> Export Excel>>Filter issue | uddeshyas@chetu.com | Discussed in morning call on Wed 2/23/2022 6:30 PM |  | Deployed only API on production | 5 hours
Unable to link Candidate on ATS with Ticket ID | anupc@chetu.com | Tue 2/22/2022 12:03 AM |  |  | 3 hours
ATS glitches | uddeshyas@chetu.com | Fri 2/18/2022 10:18 PM |  | If a candidate exits within 7 days, the ticket should reopen automatically
Data Issue | jyotid@chetu.com | Thu 2/24/2022 9:18 PM | Thu 2/24/2022 10:58 PM |  | 1.5 hours
ATS issue | pragatig@chetu.com | Monday, February 28, 2022 4:50 PM | Monday, February 28, 2022 11:25 PM |  | 2 hours
Deployed new release of ATS(QA/Staging) |  |  | Monday, February 28, 2022 11:23 PM | ATS glitch deployed on QA | 4 days
Deployed new release of ATS(production) | uddeshyas@chetu.com | `18 February 2022 22:18 | Wed 02-03-2022 21:58 | ATS glitch deployed on production
2022-03-01
Unable to Register Candidate on ATS | anupc@chetu.com | Friday, March 4, 2022 7:07 PM | Fri 04-03-2022 19:48 |  | 0.5 hours
ATS issue | uddeshyas@chetu.com | 2022-03-04 00:28 | Fri 04-03-2022 17:24 |  | 3 hours
Candidate not Found On Boarding (Offer already Accepted | anupc@chetu.com | 2022-03-04 23:29 | Mon 07-03-2022 16:37 |  | 1 hour
ATS ISSUE | jyotid@chetu.com | Thu 03-03-2022 19:46 | Mon 07-03-2022 16:49 | Information of candidate not available on OfferSection | 1 hour
ATS Issue | uddeshyas@chetu.com | Wed 09-03-2022 21:04 | Wed 09-03-2022 23:27 | Photo not visible of Chandan Das | 1 hour
Not Showing On Boarding (Offer already Accepted) | anupc@chetu.com | 2022-03-10 21:45 | Thu 10-03-2022 22:12 |  | 0.5 hours
Change Start and due date | uddeshyas@chetu.com | Tue 15-03-2022 16:50 | Tue 15-03-2022 17:51 |  | 1 hour
FW NET Tickets | uddeshyas@chetu.com | Tue 15-03-2022 21:27 |  |  | 1hour
FW: Change Start and due date | uddeshyas@chetu.com | Tue 15-03-2022 21:28 |  |  | 0.5 hours
FW Need to update the tickets | uddeshyas@chetu.com | Tue 15-03-2022 22:33 |  |  | 1 hour
RE New Changes | uddeshyas@chetu.com | Thursday, March 17, 2022 8:56 PM | Thu 17-03-2022 23:30 | 4 tickets updated | 1 hour
RE: Need Change | uddeshyas@chetu.com | 2022-03-17 21:24 | Thu 17-03-2022 23:31 | 1 ticket updated | 0.5 hour
FW Regarding ATS issue | uddeshyas@chetu.com | Mon 21-03-2022 21:04 |  | issue in tanus@chetu.com ATS details | 1 hour
RE ATS Issue ! | anupc@chetu.com | 2022-03-22 00:12 | Tue 22-03-2022 16:44 | Opening id-71352 issue | 0.5 hours
Candidate not linking ¦ ATS issue | jhalakk@chetu.com | 2022-03-23 19:20 | Wed 23-03-2022 20:25 | Opening ID 71792 issue | 0.5 hours
#70056 | uddeshyas@chetu.com | 2022-03-23 22:29 | Wed 23-03-2022 22:55 |  | 1 hour
CBT Status | tarung@chetu.com | 2022-03-29 19:53 | Wed 30-03-2022 15:52 | Resolved issue of Candidate name Govind., it’s showing “NO” in CBT Pass Section however he passed in CBT | 0.5 hour
ATS Issue ! | anupc@chetu.com | 2022-03-28 22:06 | Wed 30-03-2022 16:20 | Issue with candidate Pradhap Palani | 0.5 hour
Resource Id - 70200 | jyotid@chetu.com | 2022-03-30 20:57 | Wed 30-03-2022 23:01 |  | 0.5 hour
2022-04-01
Sumit Sharma | uddeshyas@chetu.com | 2022-04-04 17:20 | Mon 04-04-2022 18:30 | remove Sumit Sharma from ATS offer letter access. And add Anuj Garg3 | 0.5 hour
Opening ID | sonalim2@chetu.com | 2022-04-04 18:02 | Mon 04-04-2022 20:07 | Isse in Opening ID- 68696 | 0.5 hour
Not Able to Save Data | junaidh@chetu.com | Friday, April 1, 2022 7:37 AM | Mon 04-04-2022 20:18 | issue in Hiring.chetu.com | 1 hour
Unable to Offer Candidate - ATS Issue | anupc@chetu.com | 2022-04-05 15:50 | Tue 05-04-2022 16:22 | Candidate id 155736-candidate (Kritesh) is showing in hiring portal with image but when I am going to offer his details is not showing | 0.5 hour
Unable to Assign Opening - 71908 & 71910 | anupc@chetu.com | 2022-04-06 17:15 | Wed 06-04-2022 19:57 | Assigned Ticket number – 71908 to Nishant Parihar , – 71910 to Shalini B . | 1 hour
Need to check the access on review and other portals | gautamb@chetu.com | 2022-04-06 18:25 | Fri 08-04-2022 20:01 | Provided FM access | 0.5 hour
ATS issue | anupc@chetu.com | Discussed on call | Mon 11-04-2022 21:20 | Generated CBT of Candidate id 145495 | 0.5 hour
Mayank Rana | uddeshyas@chetu.com | 2022-04-13 22:21 | Wed 13-04-2022 23:08 | added mayank rana in offer letter , and remove Sonali mishra2. | 0.5 hour
ATS Issue : Candidate image not showing | anupc@chetu.com | 2022-04-14 15:14 | Thu 14-04-2022 19:41 | Issue with candidate id 156179 | 0.5 hour
Need to close | uddeshyas@chetu.com | 2022-04-11 17:03 | Thu 14-04-2022 20:47 | Closed ticket no. 69752 | 0.5 hour
Required Server for WCF deployment | itsupport <itsupport@chetu.com> | 2022-04-13 15:52 | Mon 18-04-2022 15:22 | Requested for Deployement of Outlook PlugIn Service On QA environment
ATS Issue | mayankr@chetu.com | 2022-04-18 17:21 | Mon 18-04-2022 17:42 | Issue with Opening Id 69333 | 0.5 hour
ATS Issue | mayankr@chetu.com | 2022-04-16 14:57 | Mon 18-04-2022 17:48 | Issue with Opening Id 71519 | 0.5 hour
ATS Issue : Need to fix on priority | anupc@chetu.com | 2022-04-16 21:24 | Mon 18-04-2022 19:58 | Issue with Candidate “Nitin Kumar” and 64624 (Need to close this ticket) | 2 hours
ATS Issue | jyotid@chetu.com | 2022-04-16 19:44 | Mon 18-04-2022 20:03 | Issue in Candidate id 154551 | 0.5 hour
Deployed new release of ATS(QA/Staging) | v 6.4.0.1 |  | Mon 18-04-2022 22:30 | Second Phase of AutoFollowUp module | 4.5 hours
ATS Issue | mayankr@chetu.com | 2022-04-19 16:07 | Tue 19-04-2022 17:34 | Please change the status of ticket no. 71923 from Tech Select to Offered | 0.5 hours
ATS Issue | mayankr@chetu.com | 2022-04-20 16:18 | Wed 20-04-2022 17:11 | Resolved issue of komal.varshney.2013@gmail.com | 0.5 hours
Resource Id - 70534 | jyotid@chetu.com | 2022-04-20 19:53 | Wed 20-04-2022 23:29 |  | 0.5 hour
Candidate Details - UI/UX (UI/UX) | uddeshyas@chetu.com | Fri 22-04-2022 20:47 | 2022-04-22 | Wrong result is displayed for CBT | 0.5 hour
ATS Issue | mayankr@chetu.com | 2022-04-22 18:38 | Fri 22-04-2022 22:20 | resolved issue of pspankaj02@gmail.com, rohit17vivek@gmail.com | 1 hour
Offer Accepted but not showing in Onboarding | anujg3@chetu.com | Thursday, April 21, 2022 6:12 PM | Tue 26-04-2022 19:55 | resolve five candidates records | 2 hours
ATS Issue | anupc@chetu.com | 2022-04-26 19:51 | Tue 26-04-2022 21:35 | Please find the below Employee “Zaid W” that showing On Onboarding section but not showing in weekly joining data | 0.5 hour
Hiring Portal result Required ! | anupc@chetu.com | Wed 27-04-2022 15:08 | Wed 27-04-2022 17:30 | unable to find his CBT Result on portal with Emp Id 9042 | 0.5 hour
Offer letter not Created | sonalim2@chetu.com | Thu 28-04-2022 17:17 | Thu 28-04-2022 17:59 | added sonalim2@chetu.com in offer letter mail | 0.5 hour
Avinash Kumar (212534) | tarung@chetu.com | 2022-04-28 19:03 | Thu 28-04-2022 23:00 | image of the candidate was not visible | 0.5 hour
2022-05-01
ATS update | tapans@chetu.com | Monday, May 9, 2022 6:52 PM | Tue 10-05-2022 22:35 | update the Subodh Interviewer list & previous Resourcing ticket | 0.5 hour
Hiring Portal Test ¦ Android_T | junaidh@chetu.com | 2022-05-09 17:12 | Tue 10-05-2022 20:29 | deployed test paper Android_T on hiring.chetu.com | 1 hour
Deployed new release of ATS(QA/Staging) | v 6.5.0 |  | Tue 10-05-2022 20:28 | Implemented new module EMPLOYEE DETAILS
Deployed new release of ATS(production) | v 6.5.0 |  | Thu 12-05-2022 23:31 | Implemented new module EMPLOYEE DETAILS
Regarding modification in interviewer list in ATS application | satybanr@chetu.com | discussed on call | Fri 13-05-2022 19:40 | All the FM Names with “Satyaban Ray” has now been replaced with “Ranjan Kumar” having technology as Java. | 0.5 hour
Clause Change - Offer Letter | uddeshyas@chetu.com | Thursday, May 12, 2022 10:46 PM | Mon 16-05-2022 20:24 | modified Offer letter's clause(Training and Commitment Duration) | 2 days
Offer Accepted but not showing in Onboarding | anujg3@chetu.com | Wednesday, May 11, 2022 5:16 PM | Mon 16-05-2022 23:27 | 3 offer accepted candidates are not showing on onboarding | 2 hour
CBT Report issue (218293) | tarung@chetu.com | 2022-05-26 14:22 | Thu 26-05-2022 22:32 |  | 0.5 hour
Regarding ATS | shashiy@chetu.com | 2022-05-25 20:58 | Fri 27-05-2022 16:53 | ‘’ Shubham Srivastava’’. I am not able to link his profile to the opening ID to offer . | 0.5 hour
Hiring portal not able to upload pic | tarung@chetu.com | 2022-05-27 15:48 | Fri 27-05-2022 17:11 |  | 1 hour
ATS Issue | sumitt@chetu.com | 2022-05-28 18:09 | Sat 28-05-2022 18:45 | facing issue while linking Candidate CBT Code – 217433 | 0.5 hour
Candidate not showing at Offer and Onboarding | anujg3@chetu.com | 2022-05-30 16:16 | Mon 30-05-2022 17:34 |  | 2 hours
ATS Issue | pragatig@chetu.com | 2022-05-25 19:13 | Mon 30-05-2022 19:05 | Candidate name is Venkata ( IPhone ) I can’t find him on ATS hiring portal | 0.5 hour
Details of Rajat Meena | sonalim2@chetu.com | 2022-05-31 18:21 | Tue 31-05-2022 23:24 | issue in CBT ID : 219597 | 0.5 hour
Request id 70758 | anupc@chetu.com | discussed on call | Tue 31-05-2022 23:27 |  | 0.5 hour
2022-06-01
Deployed new release of ATS(production) |  |  | Wed 01-06-2022 16:34 | Download Opening Report feature in ATS | 6 hour
ATS Issue | pragatig@chetu.com | 2022-06-01 13:47 | Wed 01-06-2022 22:22 | of Sultan Ahmed when I am trying to link the candidate his cbt result is showing as No ( --) on ATS | 0.5 hour
Deployed new release of ATS(production) |  |  | Fri 03-06-2022 . | modified Offer letter's clause(due to some discrepancy) | 1 hour
Unable to link Candidate with Ticket #70758 ! | anupc@chetu.com | 2022-06-01 21:25 | Thu 02-06-2022 20:27 |  | 0.5 hour
Change Technology | vishalg@chetu.com | 2022-06-02 21:09 | Thu 02-06-2022 22:21 | change the technology “3D” to “DevOPS” for as mention this email id vikaspathak5341@gmail.com. | 0.5 hour
Regarding ATS Issues | karthikr@chetu.com | 2022-06-01 17:25 | Fri 03-06-2022 15:17 | Issue in Verification tab | 3 hour
Candidate link issue Girraj Nirwan 220121 | tarung@chetu.com | 2022-06-04 13:13 | Mon 06-06-2022 15:02 |  | 0.5 hour
ATS Regarding | shashiy@chetu.com | Friday, June 3, 2022 8:53 PM | Mon 06-06-2022 19:05 | Candidate Sudhanshu Kaushal is showing fail in CBT | 0.5 hour
Candidate link issue Sukrit Singh Negi 219997 | tarung@chetu.com | 2022-06-06 18:46 | Mon 06-06-2022 19:07 | issue with CBT result | 0.5 hour
ATS issue | amitm2@chetu.com | 2022-06-13 20:14 | Mon 13-06-2022 22:32 | Deepak S .when I am trying to link the candidate his cbt result is showing as ( --) on ATS portal. | 0.5 hour
Deployed new release of ATS(production) | uddeshyas@chetu.com | Physical meeting done on 9-06-2022 at 10:30 PM | Fri 14-06-2022 . | modified Offer letter form. Implemented Bond Period
Candidate Linking issue on AST Kuldeep- 220776 | tarung@chetu.com | 2022-06-14 15:42 | Tue 14-06-2022 17:06 |  | 0.5 hour
ATS Issue | sukhpreetp@chetu.com | 2022-06-14 19:32 | Tue 14-06-2022 19:54 | abinpious07@gmail.com result is showing no in CBT | 0.5 hour
ATS issue | pragatig@chetu.com | 2022-06-16 19:24 | Thu 16-06-2022 22:22 | of Subash das when I am trying to link the candidate his cbt result is showing as No | 0.5 hour
ATS Issue | sumitt@chetu.com | 2022-06-11 15:29 | Thu 16-06-2022 16:02 | ranvirsinghrajput03448@gmail.com result is no in CBT | 0.5 hour
Old Tickets - Before - 10 May 2021 | uddeshyas@chetu.com | 2022-06-20 | 2022-06-22 | mark older tickets as completed | 3 hours
Sushant Anand, 218535 | tarung@chetu.com | 2022-06-20 | 2022-06-22 | CBT showing no | 0.5 hour
CBT PASS ISSUE | lovelys@chetu.com | 2022-06-21 | 2022-06-22 | CBT showing no | 0.5 hour
Linking Issue for Anubhav - 220767 | tarung@chetu.com | 2022-06-22 | 2022-06-22 | CBT showing no | 0.5 hour
Tickets to be deleted from ATS | junaidh@chetu.com | 2022-06-22 | 2022-06-24 | mark older tickets as completed | 3 hours
ATS Issue ! | anupc@chetu.com | 2022-06-22 | 2022-06-24 | Please find the below Candidates details that they joined between 6th June to 11th June . I am unable to find their data in weekly joining report . | 3 hours
ATS Issue | sumitt@chetu.com | 2022-06-28 | 2022-06-28 | CBT showing no | 0.5 hour
2022-07-01
Worked on to link the candidate on the same opening in which the candidate has been registered. The Javascript page has been modified to link the candidate and move to hiring section. |  | 2022-07-01
Worked on to apply validations on resume, image and all the other field of the candidate registration form. |  | 2022-07-01
Deployed new release of ATS(QA/Staging) |  | 2022-07-04 | 2022-07-04 | Added popup for Candidate registration in Opening module
Worked on to resolve the issue in Project Allocation stored procedure that is showing null in the technology field. |  | 2022-07-04
iOS_T ¦ CBT Test | junaidh@chetu.com | 2022-07-05 | 2022-07-05
resolved alignment issue in Opening Module |  | 2022-07-06
fixed alignment issue in Opening management |  | 2022-07-07
implemented customized filters and sorting in Opening management |  | 2022-07-08
modified alignments and validations in candidate registration |  | 2022-07-09
resolve the alignment issue in Shortlisted Candidate list |  | 2022-07-11
applied customized filter and Sorting functionality. |  | 2022-07-11
resolve the alignment issue in the Resourcing Module. |  | 2022-07-12
applied customized filter and Sorting functionality. |  | 2022-07-12
Regarding deployment in ChetuGlobalATS-INTL | uddeshyas@chetu.com | 2022-07-13 | 2022-07-14 | Added extra options in Bond Period dropdown in Offer module | 1 day
implemented Opening Allotment popup in Resourcing module. |  | 2022-07-14
implemented customized filters and sorting functionality. |  | 2022-07-14
modified stored procedure Usp_GetCandidateByEmail | uddeshyas@chetu.com | 2022-07-15 |  | modified procedures to reflect experience
modified stored procedure Usp_InsertCandidateByEmail | uddeshyas@chetu.com | 2022-07-15 |  | modified procedure to update experience
added new field Total experience in update user functionality | uddeshyas@chetu.com | 2022-07-15